## Slide 1: Status of the James Webb Space Telescope Integrated Science Instrument Module
Ray Lundquist, NASA GSFC

## Slide 2: Collaborators
Michael P. Drury
Jamie L. Dunn
Stuart D. Glazer
Matthew A. Greenhouse
Ed Greville
Gregory Henegar
Eric L. Johnson
John C. McCloskey
Raymond G. Ohl
Pam Davila
Robert A. Rashford
Gurnie C. Hobbs
Scott Lambros
Doug McGuffey
Mark F. Voyton
Vicki Balzano

## Slide 3: JWST Full Scale Model at the Baltimore Inner Harbor

## Slide 4: ISIM Subsystems
The Integrated Science Instrument Module contains
  Four Science Instruments
    NIRCam; NIRSpec; MIRI; and FGS/NIRISS
  And the supporting Infrastructure
    Primary Structure
    ISIM Electronics Compartment (IEC)
    Harness Radiator (HR)
    ISIM Command and Data Handling (ICDH)
    ISIM Remote Services Unit (IRSU)
    Thermal Control System (TCS)
    ISIM Flight Software (IFSW)
    On-Board Script System
    And Electrical Harnessing
Purge Lines and GSE Panel
ISIM Structure
Thermal Straps
NIRSpec
IEC
Radiator Baffle
Electrical
Harness and Harness Radiator
Kinematic Mount
MIRI
NIRCam
Harness Radiator

## Slide 5: Instruments are being tested and delivered
NIRCam starting vacuum testing
FGS completing vacuum testing and ready for delivery
MIRI Completed testing and delivered to Integration and Test
NIRSpec fully tested, but re-build is needed

## Slide 6: Instrument Status
Instrument | Current Testing | Upcoming Test | Delivery Date
NIRCam | Thermal/Cryo Vac | Second thermal test and vibration at GSFC | November 12
NIRSpec | Bench level assembly | Full test program | April 13
MIRI | Post ship functional | ISIM test program | Delivered (May 12)
FGS/NIRISS | Complete | ISIM test program | July 12
All NIR instrument detectors have a slow degradation process, called “hot pixels” which impacts sensitivity. Replacement detectors are being procured and will be replaced prior to the final ISIM system level test

## Slide 7: Structure
Structure delivered to I&T in 2011 after completing proof testing and cryo soak/cycle to survival temperatures
Fit check of MIRI STM and FGS ETU

## Slide 8: IEC Progress
IEC ready for acoustics test
Preparation for IEC thermal balance test
Thermal balance and moisture capture test of the IEC vent

## Slide 9: Thermal Control System
NIRS-1A
NIRS-1B
NIRS-2
Assembly
NIRS-3
Assembly
NIRS-4
Assembly
NIRS-5
Assembly
NIRSpec OA Strap - Example
Update to heat strap routing following the Return-to-Green effort
13 of 30 heat straps systems have been delivered to ISIM

## Slide 10: Electronics
ISIM remote services unit (IRSU) has been delivered and are undergoing integration verification testing
Both ISIM command data handling (ICDH) units are delivered. They have completed integration testing and are ready to support ISIM integration and test

## Slide 11: Harnesses and Harness Radiator
Electrical harnessing
  All detector interface harnesses complete and delivered
  Flight or test versions of all instrument interface cables have been completed. Final flight builds are continuing.
Aluminum Radiator Panels
Two-layer Aluminum meteoroid shields; outer layer is radiating surface
IEC (hot)
Sis – cold side
Meteoroid shield removed to show harness routing/clamps
No assembly picture yet
All piece parts received and assembly has begun

## Slide 12: Software
ISIM Flight Software
  Core software build 12.6 is complete and tested
  Initial version of all Science Instrument software applications have been successfully integrated with the Core
  Updated versions of instrument software expected with instrument delivery
  Modification of detector read-out schemes under investigation to reduce/improve system noise

## Slide 13: Test Systems
Optical simulator (OSIM) being installed in the test chamber

## Slide 14: Test Systems
ISIM level full system test configuration

## Slide 15: Summary
ISIM subsystem development is progressing well
First cryo-vacuum test planned for March 13, without NIRSpec. Two cryo-thermal tests planned with NIRSpec
NIR detector replacement plans are being developed
Test equipment, facilities, and plans are in place for a successful ISIM test program